## 2017-18
Utility Company | Location | Start Date | End Date | Closed | Overrun | Charge
Northumbrian Water | Verne Road, North Shileds | 2017-03-28 | 2017-04-03 | 2017-04-04 | 1 | 250
Northumbrian Water | ST. Peters Road North, Wallsend | 2017-04-10 | 2017-04-16 | 2017-04-17 | 1 | 250
Northumbrian Water | Gilsland Avenue, Wallsend | 2017-05-14 | 2017-05-22 | 2017-05-23 | 1 | 250
Northumbrian Water | East Forest Hall Road | 2017-05-25 | 2017-05-31 | 2017-06-01 | 1 | 250
Northumbrian Water | Norham Road | 2017-05-30 | 2017-06-08 | 2017-06-09 | 1 | 750
Northumbrian Water | Millfield Grove | 2017-06-12 | 2017-06-18 | 2017-06-19 | 1 | 250
Northumbrian Water | Woodburn Way, Whitley Bay | 2017-06-12 | 2017-06-18 | 2017-06-19 | 1 | 250
Northumbrian Water | Laburnum Avenue Lane at side and rear | 2017-06-11 | 2017-06-17 | 2017-06-18 | 1 | 250
Northumbrian Water | Crow Bank, Wallsend | 2017-06-14 | 2017-06-20 | 2017-06-21 | 1 | 250
Virgin Media | Burdon Street, North Shields | 2017-03-20 | 2017-03-31 | 2017-04-02 | 2 | 500
Virgin Media | Holyfields, West Allotment | 2017-03-29 | 2017-03-31 | 2017-04-03 | 3 | 750
Virgin Media | Banbury Way, North Shields | 2017-03-24 | 2017-04-06 | 2017-04-07 | 1 | 250
Virgin Media | Holyfields, West Allotment | 2017-04-05 | 2017-04-07 | 2017-04-09 | 2 | 500
Virgin Media | Hopper Street, North Shields | 2017-05-08 | 2017-05-19 | 2017-05-22 | 3 | 750
Virgin Media | Hopper Street, North Shields | 2017-05-08 | 2017-05-19 | 2017-05-21 | 2 | 500
Virgin Media | Hopper Street, North Shields | 2017-05-08 | 2017-05-19 | 2017-05-20 | 1 | 250
Virgin Media | Prudhoe Street, North Shields | 2017-04-26 | 2017-04-28 | 2017-04-30 | 2 | 2000
Virgin Media | West Percy Road | 2017-06-15 | 2017-06-21 | 2017-06-23 | 2 | 500
Northern Power Grid | Valley Gardens, Holy Cross | 2017-04-05 | 2017-04-20 | 2017-04-22 | 2 | 500
Northern Gas Networks | Whitley Road, Whitley Bay | 2017-04-26 | 2017-05-08 | 2017-05-09 | 1 | 750
Northern Gas Networks | Tynemouth Road, Howdon | 2017-05-30 | 2017-06-08 | N | 7 | 1750
British Telecom | Bewicke Road, Willington Quay | 2017-05-17 | 2017-05-19 | 2017-05-20 | 1 | 100
British Telecom | Clavering Street, Wallsend | 2017-05-17 | 2017-05-19 | 2017-05-20 | 1 | 250

## 2018-19
Utility | Location | Start Date | End Date | Closed | Overrun | Charge
Northumbrian Water | Hadrian Road, Wallsend | 2018-03-07 | 2018-03-13 | 2018-03-21 | 8 | 8000 | Overran by the longest period | 8 days
Northumbrian Water | The Links, Whitley Bay | 2018-03-16 | 2018-03-16 | 2018-03-23 | 7 | 9000
Northern Power Grid | John Street, Wallsend | 2018-03-13 | 2018-04-11 | 2018-04-12 | 1 | 250
British Telecom | Battle Hill Drive | 2018-05-18 | 2018-05-22 | 2018-05-23 | 1 | 250
British Telecom | Canterbury Way | 2018-05-18 | 2018-05-22 | 2018-05-23 | 1 | 250
GTC Future utilities | The Haven | 2018-05-16 | 2018-05-22 | 2018-05-24 | 1 | 250
Northumbrian Water | Charlotte Street Lane | 2018-04-18 | 2018-05-01 | 2018-05-02 | 1 | 250
Northumbrian Water | Redheugh Road | 2018-05-23 | 2018-05-28 | 2018-05-31 | 3 | 750
Northern Power Grid | Eskdale Terrace Lane | 2018-06-13 | 2018-06-19 | 2018-06-20 | 1 | 250
Northern Power Grid | Union Quay | 2018-06-11 | 2018-06-22 | 2018-06-24 | 2 | 500
Northumbrian Water | Midhurst Road | 2018-06-06 | 2018-06-12 | 2018-06-13 | 1 | 250
Northumbrian Water | Burdon Street | 2018-06-04 | 2018-06-08 | 2018-06-09 | 1 | 250
Northumbrian Water | Hartburn Road | 2018-05-30 | 2018-06-05 | 2018-06-10 | 6 | 1500
Northumbrian Water | John Street | 2018-06-06 | 2018-06-12 | 2018-06-13 | 1 | 750
Northumbrian Water | Road between Fenwicks Close Farm and Hawthorn Nurseries | 2018-06-04 | 2018-06-08 | 2018-06-10 | 2 | 500
Northumbrian Water | Laburnum Avenue Lane | 2018-06-07 | 2018-06-13 | 2018-06-14 | 1 | 250
Virgin Media | Waldo Street | 2018-06-19 | 2018-09-19 | 2018-06-20 | 1 | 250
Virgin Media | Yeoman Street | 2018-06-19 | 2018-06-20 | 2018-06-21 | 1 | 250
Northern Gas Networks | High Street East | 2018-07-16 | 2018-07-23 | 2018-07-25 | 2 | 3000
Northern Gas Networks | MCNAMARA ROAD | 2018-07-11 | 2018-07-14 | 2018-07-19 | 5 | 1000
Northern Power Grid | Salters Lane | 2018-07-26 | 2018-07-30 | 2018-07-31 | 1 | 1500
Northern Power Grid | Station Road | 2018-06-22 | 2018-07-05 | 2018-07-06 | 1 | 2350
British Telecom | Fern Driv | 2018-08-14 | 2018-08-16 | 2018-08-17 | 1 | 250
Northumbrian Water | Garth Twenty Two | 2018-08-20 | 2018-08-26 | 2018-08-27 | 1 | 250
Northumbrian Water | Gleneagles Close | 2018-08-22 | 2018-08-28 | 2018-08-29 | 1 | 250
Northumbrian Water | Newsteads Drive | 2018-08-17 | 2018-08-27 | 2018-08-28 | 1 | 250
Northumbrian Water | Rotary Road | 2018-05-04 | 2018-06-20 | 2018-06-26 | 6 | 9000
British Telecom | Station Road | 2018-10-16 | 2018-10-24 | 2018-10-26 | 2 | 4000
Northern Power Grid | Bell Street | 2018-10-15 | 2018-10-17 | 2018-10-19 | 2 | 500
Northern Power Grid | Edington Road | 2018-10-05 | 2018-10-18 | 2018-10-19 | 1 | 250
Northern Power Grid | Hartburn Road | 2018-10-05 | 2018-10-18 | 2018-10-19 | 1 | 250
Northern Power Grid | Seatonville Road | 2018-11-12 | 22/11/158 | 2018-11-23 | 1 | 2000
Virgin Media | Waterville Road | 2018-12-13 | 2018-12-19 | 2018-12-22 | 3 | 750
Northern Power Grid | Middle Street | 2019-01-15 | 2019-01-17 | 2019-01-18 | 1 | 250
Virgin Media | Wesley Way | 2019-01-16 | 2019-01-18 | 2019-01-19 | 1 | 250
Northumbrian Water | Malvern Road | 2019-02-21 | 2019-02-27 | 2019-02-28 | 1 | 250
Northumbrian Water | Monmouth Gardens | 2019-02-15 | 2019-02-21 | 2019-02-22 | 1 | 250
Northumbrian Water | Percy Park Road | 2019-02-20 | 2019-02-20 | 2019-02-22 | 2 | 900
Virgin Media | Ennerdale Road | 2019-03-06 | 2019-03-08 | 2019-03-10 | 1 | 100

## 2019-to date
Utility | Location | Start Date | End Date | Closed | Overrun | Charge
British Telecom | Pinewood Avenue | 2019-03-20 | 2019-04-01 | 2019-04-02 | 1 | 250
Northern Gas Networks | Tanners Bank | 2019-03-29 | 2019-04-08 | 2019-04-11 | 3 | 3000
Northern Power Grid | East Street | 2019-05-20 | 2019-05-23 | 2019-05-24 | 1 | 250
Northumbrian Water | Marden Road South | 2019-04-09 | 2019-05-01 | 2019-05-02 | 1 | 1800
Northumbrian Water | South View | 2019-03-04 | 2019-04-25 | 2019-04-26 | 1 | 250
Northumbrian Water | New York Way | 2019-04-23 | 2019-05-02 | 2019-05-03 | 1 | 750