## Sheet1
Project name/description | Start date | Delivery date originally specified [*1] | Actual delivery date [*2] | Planned budget | Actual spend (as at 15 Aug 2019)
A1058 Coast Road | Jan-Mar 2016 | Jun-17 | 2018-08-01 | 7204000 | 7357846
A1056 Weetslade | Feb 2016 | Mar-18 | Jun-17[*3] | 4811000 | 4260914
A191 Corridor | Jan-Mar 2016 | Dec-16 | Jun-17 | 1699000 | 1685679
A19 Employment Corridor | Apr-Jun 2016 | Dec-17 | Jan-18 | 5107000 | 5317461
North Bank of the Tyne transport scheme | Oct 2017 | Sep-18 | Works ongoing | 4478949 | 3495687
A189 Haddricks Mill to West Moor | Sep 2018 | Feb-20 | Works ongoing | 5473850 | 2309234
Cobalt Cycle Scheme | Jan 2017 | Mar-17 | Aug-17 | 650000 | 731625
Coast Road Cycle Scheme | Spring 2016 | n/a [*4] | 2019-08-01 | 1484000 | 1561883
*1 - In construction terms, the planned delivery date for each of the projects is the same as the actual delivery date, since changes to the project timescale were approved through the contractual process.
*2 - Refers to completion of main works on site.
*3 - Actual delivery date of the works delivered by North Tyneside Council. The project also includes developer-funded works which are to be delivered at a later date.
*4 - This project was funded as part of a wider package and hence no delivery date was formally specified.